## P0 Task Tracker
# | Feature | Task | Description | Implementation Type | Status | Blocked By | Reference Files | Notes
1 | Audit Logging Schema | Design audit record schema | Every query RegOS processes needs a structured audit trail for regulatory compliance. This task defines the data model: what fields each audit record contains (query text, user ID, timestamp, retrieval results, citations used, confidence score, escalation status, guardrail triggers). Getting the schema right first means every feature built after this can emit audit records as it's developed, instead of retrofitting logging later. | DB Model + Router | Complete |  | audit_logger.md audit_logger.py README.md (functions folder) | Complete. audit_logger.py v0.4.0 — schema has 26 fields including confidence_score, confidence_signals, escalation, guardrail columns. SQLite DB at /app/backend/data/audit.db. The MD file (audit_logger.md) was enriched from 327 → 982 lines covering every field, the inlet/outlet lifecycle, and the HTML comment bridge protocol that connects GraphRAG → audit.
|  | Create SQLAlchemy model and migration | Translate the audit schema design into an actual database table using SQLAlchemy (the ORM Open WebUI uses). Create an Alembic migration so the table is automatically created when the app starts. This gives us a persistent store for audit records that survives restarts and can be queried. | DB Model | Complete |  | audit_logger.py (lines 1–80) audit_logger.md § Database Layer | Complete. Deliberate decision: SQLite directly, NOT SQLAlchemy/Alembic. Matches Open WebUI's own filter pattern. CREATE TABLE IF NOT EXISTS runs on first import — no migration needed. Separate DB from Open WebUI's webui.db so audit data survives Open WebUI upgrades and can be managed independently for compliance lifecycle.
|  | Build audit record persistence layer | Build the Python service layer that other features call to write audit records. This is a simple interface: pass in a dict of audit data, get back a stored record. Kept separate from Open WebUI's main database so audit data has its own lifecycle and can be managed independently for compliance purposes. | Backend Service | Complete |  | audit_logger.py — inlet() and outlet() audit_logger.md § Persistence Layer | Complete. Two-phase write: inlet() creates record with user_id, query, timestamp. outlet() matches by user_id + empty response field and UPDATEs with LLM response, confidence data, guardrail flags. Key design choice: matching uses user_id (not query text) to handle edits/retries. Tested with concurrent users — no collision issues in SQLite WAL mode.
|  | Build admin API for querying audit records | Create a REST API endpoint (GET /api/audit/records) that lets administrators search and retrieve audit records by query ID, user ID, date range, or escalation status. For P0 this is a basic filtered query API — the full chat-based audit interface is P2. But the data needs to be accessible from day one. | API Router | Partial |  | audit_logger.md § Querying Audit Records breach_api.py (planned) | Partial. No REST endpoint yet — deferred to P1. Records queryable now via SQLite CLI: docker exec open-webui sqlite3 /app/backend/data/audit.db "SELECT * FROM audit_records ORDER BY id DESC LIMIT 10;". The MD doc has SQL patterns for common queries: by user, by date range, by escalation status, by confidence band. Sufficient for demo.
2 | GraphRAG Pipe | Build entity linker | When a user types a question like 'What are the effluent limits under Chapter 24?', the system needs to extract the regulatory entities from that natural language: section references (Chapter 24), defined terms (effluent limits), obligation types, and jurisdictions (Miami-Dade). This is the first step of graph-guided retrieval — without it, we can't query Neo4j intelligently. Implementation is either a small NLP model or an LLM call with a structured extraction prompt. | Pipe Function | Complete |  | graphrag_filter.md § Entity Search & Linking graphrag_filter.py — _search_entities() graphrag_vs_rag.md | Complete. graphrag_filter.py v0.16.0 — fulltext entity search on 738 Entity nodes in Neo4j. Uses CALL db.index.fulltext.queryNodes() with Lucene character escaping and min_relevance_score filtering. v0.15.0 added facility context disambiguation with _FACILITY_CONTEXTS mapping and _disambiguate_thresholds(). graphrag_vs_rag.md (expanded 75 → 333 lines) shows real A/B test results proving graph entity linking beats pure vector search.
|  | Build Cypher query generator | Once we have extracted entities (section refs, terms, jurisdictions), we need to translate them into Cypher queries that Neo4j can execute. For example, if the entity linker finds 'Chapter 24, Section 42' and 'effluent discharge', the generator produces a parameterized Cypher query that traverses the graph to find that section, its definitions, cross-references, and applicable exceptions. This replaces the current approach where we skip the graph entirely. | Pipe Function | Complete |  | graphrag_filter.md § Cypher Query Construction graphrag_filter.py — _search_entities(), _get_sections_for_entities() | Complete. Parameterized Cypher — not a dynamic generator, but covers all P0 query patterns. _search_entities() issues fulltext index queries. _get_sections_for_entities() traverses Entity→MENTIONS→Episodic relationships via MATCH patterns. Decision rationale: dynamic Cypher generation is fragile and error-prone; parameterized queries are testable and predictable.
|  | Build Neo4j traversal and graph candidate filtering | Execute the generated Cypher queries against Neo4j and collect the results into a candidate set of regulatory content. This is the structural retrieval step — it finds content that is structurally relevant (parent sections, linked definitions, cross-referenced exceptions) rather than just semantically similar. The graph already contains Chapter 24 with document-section relationships, jurisdiction tagging, and version tagging. This task wires the Pipe to actually use it. | Pipe Function | Complete |  | graphrag_filter.md § Graph Traversal graphrag_filter.py — _get_sections_for_entities() GRAPH_REBUILD_QUICKSTART.md | Complete. _get_sections_for_entities() returns sections with matched_entities list and entity_count. Results ordered by entity overlap count — sections matching more query entities rank higher. This is the structural retrieval step (finds content by relationship, not just semantic similarity). GRAPH_REBUILD_QUICKSTART.md covers rebuilding the Neo4j graph from scratch.
|  | Wire ChromaDB semantic ranking on graph-filtered candidates | The graph gives us structurally relevant candidates, but we still need semantic ranking to surface the most relevant chunks for the specific question asked. This task takes the graph candidate set and scores it against the user's question using ChromaDB's existing vector embeddings and the bge-reranker. The result is a hybrid retrieval pipeline: graph for structural relevance, vectors for semantic relevance. | Pipe Function | N/A for P0 |  | graphrag_filter.md § Hybrid Retrieval graphrag_vs_rag.md § Why No ChromaDB Re-ranking | N/A for P0. ChromaDB re-ranking deferred. Instead, Open WebUI's built-in Knowledge Base (KB) handles vector search separately, and GraphRAG provides structural context. The two compound via dual context injection: graph context prepended to user message, KB context via RAG. graphrag_vs_rag.md shows this hybrid approach outperforms either alone in test cases.
|  | Build context and citation assembly | Package the ranked retrieval results into a structured context payload for the LLM. Each chunk gets full citation metadata attached: section number, section title, jurisdiction (Miami-Dade County), document name (Chapter 24), document version (v2026-01-05). This metadata flows through to the final response so every claim in the answer is traceable to a specific regulatory source. | Pipe Function | Complete |  | graphrag_filter.md § Context Assembly graphrag_filter.py — _assemble_context() | Complete. _assemble_context() deduplicates sections, truncates to fit context window, builds [G1]–[G5] citation blocks. Section refs extracted from source_description field. Each citation carries: section number, section title, document ref (Chapter 24). The [G] prefix distinguishes graph citations from Open WebUI's KB citations so the LLM can attribute correctly.
|  | Build answer validation layer | Before returning the LLM's response to the user, validate that it's consistent with what the graph told us. Check that all sections, definitions, and exceptions identified by the graph traversal are actually referenced in the answer. Flag any dangling citations (references to sections that weren't in the retrieval set) or missing cross-references. If gaps are found, re-query to fill them. This prevents the LLM from hallucinating citations. | Pipe Function | N/A for P0 |  | graphrag_filter.md § Answer Validation confidence_scoring.md | N/A for P0. Full answer validation (parsing LLM output, cross-checking against graph results) deferred to P1. Confidence scoring (Feature 3) serves as the proxy — it tells you how good the retrieval was, which strongly correlates with answer quality. Full validation would require a second LLM call to parse/check, adding latency and cost.
|  | Build jurisdiction isolation enforcement | The graph must enforce jurisdiction boundaries at query time. If a user is asking about Miami-Dade County regulations, the Cypher queries must filter to Miami-Dade only — no content from other jurisdictions can leak into the results. For P0 we only have Miami-Dade, but this enforcement must be built now so that adding jurisdictions later doesn't require rearchitecting the retrieval pipeline. | Pipe Function | Complete |  | graphrag_filter.md § Jurisdiction Isolation GRAPH_REBUILD_QUICKSTART.md | Complete by default — only Miami-Dade Chapter 24 data in Neo4j. Graph schema already supports multi-jurisdiction via node properties (jurisdiction field on Section/Entity nodes). When a second jurisdiction is added, the Cypher queries need a WHERE clause filter. The architecture is ready; the filter just doesn't activate yet because there's only one dataset.
|  | Instrument audit logging across the query chain | Wire each step of the GraphRAG pipeline to emit data to the audit record: which entities were extracted, what Cypher was generated, what Neo4j returned, how candidates were ranked, what context was assembled, what the LLM produced, what validation found. This gives full provenance for every answer — you can trace exactly how any response was generated. | Pipe Function | Complete | Audit Schema | graphrag_filter.md § Audit Integration audit_logger.md § Data Bridge graphrag_filter.py — outlet() | Complete. GraphRAG outlet() injects confidence signals into the LLM response via hidden HTML comment: <!-- GRAPHRAG_CONFIDENCE:{"score":0.73,"band":"MEDIUM","signals":{...}} -->. audit_logger.py outlet() regex-extracts this JSON and writes confidence_score (REAL) + confidence_signals (JSON TEXT) to audit_records. The HTML comment is invisible to the user but parsed by the audit logger before final response delivery.
|  | Load-test hybrid pipeline for acceptable latency | The hybrid graph+vector pipeline adds steps compared to the current vector-only retrieval. Run a set of representative queries and measure end-to-end latency. Identify bottlenecks (Neo4j query time, ChromaDB re-ranking, LLM generation). The target is a response time that feels interactive for a demo — if it's too slow, optimize the Cypher queries or reduce the candidate set size. | Testing | Complete |  | graphrag_filter.md § Performance Testing graphrag_vs_rag.md § Latency Benchmarks | Complete. 5-query benchmark results: BOD=826ms, Pretreatment=983ms, Vague query=736ms, Everglades=1788ms (worst case — broad topic pulls many entities), Hello=fast (guardrail short-circuit, no graph query). All within interactive demo range. Bottleneck is Neo4j fulltext search, not filter logic. Acceptable for P0 demo — optimization deferred to P1.
3 | Confidence Scoring | Define scoring signals and weights | The system needs to compute a confidence score on every response that tells the user (and the escalation system) how reliable the answer is. This task defines which signals feed into that score: retrieval relevance scores from ChromaDB, coverage completeness (did the graph find all expected cross-references?), graph dependency satisfaction (were all structural relationships resolved?), reranker scores. Also defines how to weight them into a composite number. Requires alignment with Soham on the approach. | Design | Complete | GraphRAG Pipe | confidence_scoring.md graphrag_filter.md § Confidence Scoring graphrag_filter.py — _calculate_confidence() | Complete. 6 weighted signals: avg_entity_score (0.25), entity_count (0.15), max_entity_overlap (0.25), section_count (0.15), has_graph_exclusive (0.10), avg_direct_score (0.10). Bands: HIGH ≥ 0.8, MEDIUM ≥ 0.5, LOW < 0.5. Weights were tuned against the 5-query benchmark set. confidence_scoring.md (enriched to 265 lines) is the definitive reference with rationale for each signal and weight.
|  | Build composite scoring function inside the Pipe | Implement the agreed-upon scoring formula as a function within the GraphRAG Pipe. It runs after retrieval and validation (Step 8 of the chain), takes the retrieval quality signals as input, and outputs a confidence score between 0 and 1. This score is attached to the response metadata and used by both the enterprise template (to display) and the escalation workflow (to trigger). | Pipe Function | Complete |  | graphrag_filter.py — _calculate_confidence() confidence_scoring.md § Implementation | Complete. _calculate_confidence() runs after _get_sections_for_entities(). Stores results on self._confidence_score, self._confidence_band, self._confidence_signals. Test scores: BOD=0.73 (MEDIUM), Everglades=0.67 (MEDIUM), vague=0.58 (MEDIUM), hello=0.0 (LOW — triggers guardrail). The 0.5 MEDIUM boundary was chosen so that any query with at least one entity match and one section hit gets above LOW.
|  | Emit confidence score to audit record | Write the computed confidence score and the individual signals that composed it (relevance scores, coverage, etc.) to the audit record for this query. This creates an auditable trail of why a particular confidence was assigned, which is important for regulatory compliance — you need to explain your system's reasoning, not just its answer. | Pipe Function | Complete | Audit Schema | audit_logger.md § Confidence Fields graphrag_filter.py — outlet() audit_logger.py — outlet() | Complete. Bridge protocol: graphrag_filter.py outlet() embeds <!-- GRAPHRAG_CONFIDENCE:{JSON} --> in response → audit_logger.py outlet() regex-extracts → writes confidence_score (REAL column) and confidence_signals (TEXT column, full JSON blob) to audit_records. Audit trail shows exactly which signals drove each confidence score. Verified with diag_hash2.py diagnostic during SHA-256 debugging session.
4 | Enterprise Output Formatting | Design enterprise response template | Currently, answers appear as plain text in a chat bubble. For a utility compliance demo, every response needs a standardized professional format: a one-line compliance determination at the top (Compliant / Non-Compliant / Requires Review), a citation block listing each regulatory section with its metadata, a confidence score badge, an escalation indicator if triggered, and a structured refusal block when the system can't answer. This task defines that template layout. | Design | Not Started |  | RegOS_Enterprise_Formatting_Progress_Report.docx graphrag_filter.md § Enterprise Formatting system_prompt.md | Not Started. Template design direction documented in RegOS_Enterprise_Formatting_Progress_Report.docx. Currently, structured output is handled entirely via system_prompt.md instructions (LLM formats its own response with compliance determination, citations, confidence). No programmatic template rendering yet. This is a P0 gap — demo relies on prompt-based formatting only.
|  | Build backend formatting logic in the Pipe outlet | Add formatting logic to the GraphRAG Pipe that takes the raw LLM response plus all the metadata (citations, confidence score, escalation status) and structures it into a formatted output — either styled markdown or structured JSON that the frontend component can render. This ensures every response leaving the backend already has the enterprise template applied. | Pipe Function | Not Started | Confidence Scoring | graphrag_filter.py — outlet() graphrag_filter.md § Outlet Processing | Not Started. outlet() currently handles: (1) confidence signal injection via HTML comments, (2) audit data bridging. Enterprise template logic will be a third layer in outlet() that wraps the LLM response with structured sections: compliance header, citation block, confidence badge, escalation banner. graphrag_filter.md § Outlet Processing documents the current flow.
|  | Build Svelte frontend component for structured response rendering | Create a custom Svelte component in the chat message area that recognizes the structured enterprise response format and renders it with proper visual hierarchy: colored status badges for the determination, collapsible citation blocks, a confidence gauge or score display, and an escalation banner. This is what makes the demo look like enterprise software rather than a chat toy. | Frontend Component | Not Started |  | RegOS_Enterprise_Formatting_Progress_Report.docx graphrag_filter.md § Frontend Integration (planned) | Not Started. Requires custom Svelte component in Open WebUI frontend. Planned visuals: colored status badges (green/amber/red), collapsible citation blocks, confidence gauge/score display, escalation banner. Blocked on backend template (row 19) being built first. RegOS_Enterprise_Formatting_Progress_Report.docx has the design mockups.
5 | Escalation Workflow | Build case packet generator | When a response has low confidence or involves a high-risk compliance area, the system needs to bundle everything a reviewer would need to assess it: the original question, the full retrieval set (which chunks were pulled and their scores), all citations, the confidence score and its breakdown, the draft response, and a recommended action. This task builds that bundling logic inside the Pipe, using data that already exists at that point in the chain. | Pipe Function | Not Started | Confidence Scoring | N8N_ESCALATION_SETUP.md regos_escalation_workflow.json graphrag_filter.md § Escalation | Not Started. The n8n workflow already exists (regos_escalation_workflow.json) and routes low-confidence answers to APAS team. Case packet generator will bundle: original query, full retrieval set with scores, all citations, confidence score + signal breakdown, draft response, recommended action. All this data already exists in the GraphRAG pipeline by the time outlet() runs — just needs packaging.
|  | Add configurable confidence threshold as a Valve | The confidence score below which escalation triggers should be adjustable by administrators, not hardcoded. Open WebUI has a built-in Valve system for admin-configurable settings on functions. This task adds a threshold Valve to the GraphRAG Pipe so admins can set it per workspace — a utility with strict compliance requirements might want a higher threshold than one with more flexibility. | Pipe Function | Not Started |  | graphrag_filter.py — class Pipe (Valves section) graphrag_filter.md § Valves (Admin Settings) | Not Started. Open WebUI Valves = admin-configurable settings per function. graphrag_filter.py already has Valves for: neo4j_uri, neo4j_user, neo4j_password, model_id, context_window. Adding confidence_threshold Valve is straightforward — same pattern. Default 0.5 (MEDIUM boundary). A strict utility might set 0.7; a flexible one might accept 0.4.
|  | Upgrade n8n pipeline to accept structured case packet | An n8n escalation node already exists that routes low-confidence answers to the internal APAS team. Currently it just sends the response text. This task upgrades it to receive and attach the full structured case packet, so reviewers get the complete context (query, retrieval set, citations, confidence, recommendation) instead of just the answer. | n8n Pipeline | Not Started |  | N8N_ESCALATION_SETUP.md regos_escalation_workflow.json apas_bridge.py | Not Started. Current n8n node sends plain response text only. Upgrade: modify webhook payload to include full case packet JSON (query, retrieval set, citations, confidence, recommendation). apas_bridge.py is the planned API bridge between Open WebUI and the internal APAS review system. N8N_ESCALATION_SETUP.md has the webhook config and workflow diagram.
|  | Render escalation indicator in enterprise response template | When escalation is triggered, the user needs to see a clear visual indicator in the response telling them this answer has been flagged for expert review. This task adds that indicator to the enterprise frontend component — a banner or badge that says the response is under review, so the user knows not to treat it as a final determination. | Frontend Component | Not Started | Enterprise Formatting | RegOS_Enterprise_Formatting_Progress_Report.docx graphrag_filter.md § Escalation (planned) | Not Started. Blocked on Feature 4 (Enterprise Formatting). The "Under Expert Review" banner will be part of the enterprise response template — triggers when confidence < threshold OR high-risk regulatory area detected. The docx report shows the planned banner design. Cannot build without the template infrastructure from Feature 4.
6 | Threshold Evaluation | Curate machine-readable threshold table from Chapter 24 | Chapter 24 contains regulatory limits (e.g., maximum effluent discharge levels, pH ranges, temperature limits) expressed in legal language. This task extracts those into a structured, machine-readable table: parameter name, limit value, unit, comparison operator, and the exact Chapter 24 clause reference. This is a manual data curation task, not code — someone reads the regulation and builds the table. It can be done in parallel with Features 1-5. | Data Task | Not Started |  | regulatory_thresholds.json graphrag_filter.md § Threshold Data Model Chapter 24/ (source regulation) | Complete. regulatory_thresholds.json contains all machine-readable thresholds from Chapter 24. Each entry: parameter, value (STRING — e.g., "30", "15.0"), unit, direction (max/min), section_ref, description. Important: values stored as strings, normalized to float at runtime via float(str(item["value"]).replace(",","")). Manual data curation task — read the regulation, built the table.
|  | Build threshold evaluation service | A standalone Python service that receives normalized sensor readings from the Pump Station Ontology pipeline, looks up the applicable regulatory threshold from the curated table, and determines whether the reading is compliant or non-compliant. On breach, it records: the reading value, the threshold value, the exact clause reference, and a timestamp. This runs as a background process, independent of the chat interface. | Standalone Service | Not Started | Pump Station data | graphrag_filter.py — _evaluate_thresholds(), _perform_threshold_evaluation() graphrag_filter.md § Threshold Evaluation Engine threshold_eval.py | Complete. Built directly into graphrag_filter.py v0.16.0 (not a separate service). _evaluate_thresholds() loads regulatory_thresholds.json, normalizes values, applies direction-aware comparison: max → user ≤ threshold, min → user ≥ threshold. Records each determination with parameter, values, status (COMPLIANT/BREACH/NEEDS_CLARIFICATION), timestamp, section_ref. Results stored in SQLite: /app/backend/data/regos_breaches.db. v0.15.0 added NEEDS_CLARIFICATION for ambiguous facility contexts.
|  | Implement SHA-256 evidence hashing for each determination | Every threshold evaluation determination (compliant or non-compliant) gets a SHA-256 hash computed over its contents (reading, threshold, clause, timestamp). This creates tamper-evident evidence — if anyone changes the record after the fact, the hash won't match. Required for regulatory audit integrity. | Standalone Service | Not Started |  | graphrag_filter.py — _store_threshold_evaluation() (evidence_hash logic) graphrag_filter.md § SHA-256 Evidence Hashing verify_hashes.py RegOS_SHA256_Demo.docx demo_show_records.py, demo_tamper.py, demo_reset.py | Complete. SHA-256 hash over 8 fields: parameter, user_value, threshold_value, threshold_direction, threshold_unit, status, timestamp, section_ref. Uses json.dumps(sort_keys=True, separators=(",",":")) — compact JSON, sorted keys. Hash stored in evidence_hash column. CRITICAL: separators must be (",",":") not default, or hash won't match (root cause of the TAMPERED bug we debugged). verify_hashes.py = production verification script. RegOS_SHA256_Demo.docx = CEO-facing 7-page demo walkthrough with 4-step live demo. demo_show_records.py / demo_tamper.py / demo_reset.py = Docker demo scripts.
|  | Register breach query Tool for the chat | Create an Open WebUI Tool (a callable function the LLM can invoke) with functions like get_active_breaches(), get_breach_history(station_id), get_threshold_for_parameter(). This lets users ask the chat questions like 'Are there any active breaches at Station 5?' and get answers backed by real sensor evaluation data, not just regulatory text. | Tool Function | Not Started |  | graphrag_filter.py — _check_active_breaches() graphrag_filter.md § Breach Query Tool breach_api.py (planned) | Partial. _check_active_breaches() built into graphrag_filter.py — queries regos_breaches.db. LLM can invoke it contextually when users ask about breaches. A formal Open WebUI Tool registration (get_active_breaches(), get_breach_history(), get_threshold_for_parameter()) not yet implemented — that would let the LLM call these functions explicitly via tool_use. Current approach works but relies on the filter detecting breach-related queries.
|  | Build API endpoint for dashboard to pull breach data | The dashboard (Feature 7) needs a REST API to fetch current breach status, active alerts, and compliance posture. This task creates that endpoint, pulling from the threshold evaluation service's data store. Separate from the chat Tool — this is for the frontend dashboard to consume directly. | API Router | Not Started |  | breach_api.py (placeholder) graphrag_filter.md § Breach API | Not Started. breach_api.py exists as a placeholder file. Will expose REST endpoints: GET /api/breaches/active, GET /api/breaches/history/{station_id}, GET /api/breaches/parameter/{param_name}. Data source is regos_breaches.db. Needed by Feature 7 (Dashboard) to render breach data in the frontend.
7 | Dashboard | Design dashboard layout | The dashboard is the first thing a utility prospect sees in the demo. It needs to show at a glance: overall compliance posture (green/amber/red), a list of active regulatory breaches with severity and clause references, and an embedded chat for follow-up questions. This task designs the layout, component structure, and data flow. For P0 it's a single-page functional view — no navigation, settings, or admin features needed. | Design | Not Started |  | graphrag_filter.md § Dashboard Integration (planned) RegOS_Enterprise_Formatting_Progress_Report.docx | Not Started. Single-page Svelte view for demo: compliance posture hero (green/amber/red), active breach list with severity and clause refs, embedded chat. No navigation, settings, or admin features for P0. RegOS_Enterprise_Formatting_Progress_Report.docx has some design direction. Requires breach API (Feature 6) to be built first.
|  | Build compliance status summary component | A Svelte component that displays green/amber/red indicators showing current compliance posture against Chapter 24 obligations. It consumes data from the threshold evaluation engine's API. Green means all readings within limits, amber means approaching thresholds, red means active breaches detected. This is the hero visual of the dashboard. | Frontend Component | Not Started | Threshold Evaluation | regulatory_thresholds.json breach_api.py (planned) | Not Started. Blocked on Feature 6 threshold evaluation + breach API. Component logic: green = all readings within limits, amber = within 10% of threshold (proximity calc not yet implemented), red = active breach (status=BREACH in regos_breaches.db). Consumes data from threshold engine API.
|  | Build active breach alerts component | A Svelte component that lists currently active regulatory violations: which parameter breached, which clause was violated, the severity level, and when it was detected. Each alert links back to the specific Chapter 24 section. This gives the prospect immediate visibility into what's wrong and where to look. | Frontend Component | Not Started | Threshold Evaluation | regulatory_thresholds.json breach_api.py (planned) | Not Started. Blocked on Feature 6. Each alert row: parameter name, breached value vs threshold value, violated clause (section_ref from regulatory_thresholds.json), severity level, detection timestamp. Section_ref links back to Chapter 24 text.
|  | Embed chat interface within the dashboard | Integrate the existing Open WebUI chat component (which now runs the GraphRAG Pipe) directly into the dashboard page. The prospect should be able to see a breach alert and immediately ask a follow-up question like 'What are my obligations under this clause?' without switching screens. This reuses the existing chat component — no new chat logic needed. | Frontend Component | Not Started | GraphRAG Pipe | graphrag_filter.md § Open WebUI Integration system_prompt.md | Not Started. Open WebUI's chat component can be embedded via Svelte component composition. GraphRAG filter + system prompt already configured for chat. This task just wires existing chat into the dashboard page — no new chat logic. system_prompt.md defines the LLM's regulatory compliance persona and response format.
8 | Refusal & Guardrails | Format refusal output to use enterprise response template | Refusal already works — when the system can't answer, it says so and recommends an alternative. But currently the refusal is plain text in a chat bubble. This task formats refusals using the enterprise template (Feature 4): a structured refusal block explaining what information is missing and a specific, actionable recommendation (e.g., 'Consult Section 24-42 directly' or 'Escalated to licensed reviewer'). | Pipe Function | Not Started | Enterprise Formatting | graphrag_filter.md § Guardrails & Refusal system_prompt.md RegOS_Enterprise_Formatting_Progress_Report.docx | Not Started. Refusal works today via system prompt — LLM refuses and recommends alternatives. But it's plain text in a chat bubble. This task adds structured formatting: what info is missing, specific actionable recommendation (e.g., "Consult Section 24-42 directly"), escalation offer. Blocked on Feature 4 enterprise template.
|  | Add hard guardrails in Pipe | In addition to the LLM's system-prompt-based refusal, add programmatic guardrails in the GraphRAG Pipe. If the graph traversal returns zero relevant sections, or if the jurisdiction doesn't match any ingested regulation, the Pipe short-circuits and returns a structured refusal directly — without calling the LLM at all. This is more reliable than depending on the LLM to refuse correctly every time. | Pipe Function | Not Started | GraphRAG Pipe | graphrag_filter.py — inlet() graphrag_filter.md § Hard Guardrails adversarial_guardrails.md | Not Started. Planned hard guardrails: (1) zero graph results → structured refusal, no LLM call, (2) jurisdiction mismatch → immediate refusal, (3) off-topic detection → short-circuit. These are programmatic (in the Pipe), not LLM-dependent. More reliable than system-prompt-only refusal. adversarial_guardrails.md has the planned test cases. This is a P0 gap — currently guardrails are soft (prompt-based) only.
|  | Instrument guardrail triggers to emit audit records | Every time a guardrail fires (refusal, jurisdiction boundary enforcement, out-of-scope detection), write it to the audit record. This creates a log of what the system refused to answer and why, which is critical for demonstrating to regulators that the system behaves conservatively and doesn't make unsupported claims. | Pipe Function | Not Started | Audit Schema | audit_logger.md § Guardrail Fields audit_logger.py — outlet() graphrag_filter.md § Guardrail Audit Trail | Not Started. audit_logger.py schema already has the columns: guardrail_triggered (BOOLEAN), guardrail_type (TEXT), guardrail_reason (TEXT). When hard guardrails are built (row 35), they emit data to these fields. The schema is ready — just needs the guardrail logic to populate it. Critical for demonstrating conservative system behavior to regulators.
|  | Build and run adversarial test suite | Create a set of 20+ test queries specifically designed to break the guardrails: questions outside the ingested knowledge, attempts to mix jurisdictions, prompts that try to get the system to cite non-existent sections, questions that push the system to speculate beyond its data. Run them all and verify zero hallucinations. This is the final validation that the system behaves correctly under adversarial conditions. | Testing | Not Started |  | adversarial_guardrails.md graphrag_vs_rag.md § Edge Cases disclaimer_research.md | Not Started. adversarial_guardrails.md defines 20+ test cases: jurisdiction mixing (ask about Broward County when only Miami-Dade is loaded), citation fabrication ("cite Section 99-999"), speculation prompts ("what will the limits be next year?"), cross-regulation confusion, authority impersonation. graphrag_vs_rag.md § Edge Cases has preliminary results from RAG comparison testing. disclaimer_research.md covers legal framing for refusal responses. Target: zero hallucinations across all test queries.