## P1-P2 Feature Backlog
RegOS — Deferred Features (P1 / P2 / Future)
Post-meeting update (Mar 2, 2026). Items 4+5 merged into 3. GIS scope rewritten. Time-Decay deferred. API Exposure + NotebookLM Benchmark added.
# | Feature | Description (Plain English) | Phase | Category | Current State in P0 | What Was Planned | Source Document | Complexity | Owner | Senior Feedback (2nd Mar) | Task / Subtask | Deadline
1 | Compliance Dashboard UI | A visual dashboard that shows at a glance whether the facility is meeting all regulatory requirements — green for compliant, amber for borderline, red for violations. | P2 | Frontend / Visualization | Deprioritized. Replaced by SCADA Streaming API (v0.1.0) as primary integration point. No UI exists. | Single-page dashboard showing: compliance status (green/amber/red), active breach alerts list, embedded RegOS chat interface, aggregated trend charts. Would consume data from threshold evaluation API, breach DB, and audit records. | P0_Feature_Analysis.md (lines 163-186) REGOS_CHANGELOG.md (line 297) | Large | Shreya | This is in Shreya's ballpark, leave it to the team to have a turnaround by 5th March regarding this. APAS needs to have a ubiquitous UI going forward. | • DO NOT TOUCH — Shreya leads UI/UX direction | 5th March (direction from team)
2 | Chat-Based Audit Query Interface | Instead of running database queries, users can simply ask questions in plain English like "Show me all queries from last week" and get audit results back in a chat conversation. | P2 | Audit / UX | Basic REST API exists (GET /api/audit/records with query_id, user_id, date_range filters). Terminal/API-only access. | Full conversational interface for querying audit logs. Users would ask natural-language questions like “Show me all escalated queries from last week” and get structured results in the chat. Would require a dedicated Open WebUI Tool or Pipe that queries the audit SQLite DB. | P0_Feature_Analysis.md (line 154) | Medium | Anmol | Accepted | • Create Open WebUI Tool/Pipe for audit DB queries | TBD (P2)
3 | Escalation Workflow (Manual Trigger + Resolution + Routing) | When the AI is unsure about an answer, a human expert can be notified via email to review it. This includes a button in chat to manually flag a response, plus a system to track and resolve flagged cases. | P1 | Escalation Workflow | Only automatic escalation exists (confidence < 0.65). Cases go to n8n webhook but never come back as resolved. n8n Branch 1 ends with No-Op placeholder. Response captured but not displayed to users. | Two-phase approach. Phase 1: simple email escalation button (font-awesome icon next to thumbs up/TTS in response subtext panel) that emails sysadmin1@regos.ai with chat context. Uses chat_ID for traceability. Phase 2: full Jira integration (3 free seats, lifetime) — push entire chat context + form + relevant docs into Jira helpdesk. Case lifecycle: Open → In Review → Resolved → Closed. Display resolution status back to user via status API. | REGOS_CHANGELOG.md (lines 257, 259) N8N_ESCALATION_SETUP.md (lines 205, 207-216) | Medium | Anmol | Create an font-awesome icon in the subtext panel of the response. (Next to thumbs up, TTS button etc). As discussed earlier only use the chat_ID maintained by the system for traceability. Exit system can be decided (No JIRA for now, Bloodhound-like can be debated) [Old #4 — Escalation Resolution]: Accepted [Old #5 — n8n Case Routing]: This is dependant on resolution of point 3 feedback. If we are using an issue resolution tool this is redundant. We need to integrate status API into APAS AI for display that's it. [Old #6 — n8n Escalation Response Enhancement]: This is a 2-step simple orchestration please truncate into point4. | • Phase 1: Email escalation button | Phase 1: 7th March Phase 2: 14th March
4 | Multi-Jurisdiction Support | Right now the system only knows Miami-Dade County rules. This feature would let it understand regulations from other counties, states, or jurisdictions so it can serve a wider customer base. | P2 | Knowledge Graph / Core | System is scoped exclusively to Miami-Dade County Chapter 24. Jurisdiction guardrail blocks non-Miami-Dade queries. | Support multiple regulatory jurisdictions (other Florida counties, other states, federal EPA). Would require: separate knowledge graphs per jurisdiction, jurisdiction detection and routing in inlet, cross-jurisdiction comparison queries, per-jurisdiction confidence thresholds, jurisdiction-specific threshold tables. | REGOS_CHANGELOG.md (line 318) adversarial_guardrails.md (line 120) | Very Large | TBD | Accepted, Please engage with stakeholders to define future scope. | • Stakeholder engagement to define future scope | TBD (P2)
5 | Advanced Prompt Injection Defense + Smarter Guardrail Keyword Matching | Protection against users trying to trick the AI into ignoring its rules or giving incorrect answers. Also makes the system smarter about recognizing which questions are actually about regulations vs. off-topic. | P1 | Guardrails / Security | Prompt injection defense relies entirely on system prompt instructions. No hard programmatic defenses. Keyword matching is blunt — “building code” triggers even if user asks about Chapter 24 facilities near buildings. | Add programmatic injection detection: pattern matching for common injection techniques, input sanitization layer before graph search, canary token detection, output validation. Replace simple substring matching with context-aware detection: NLP-based intent classification, phrase boundary awareness, configurable false-positive tolerance. | adversarial_guardrails.md (lines 118, 122-123) | Medium | Anmol | This is an advanced guardrail please debate it's ease of deployment with me and either implement before end of business 10th March or defer for P2. [Old #9 — Smarter Guardrail Keyword Matching]: Accepted, please truncate to point8 | • Debate ease of deployment — implement by EOB 10th March or defer P2 | 10th March EOB (or defer to P2)
6 | Neo4j Failover for Zero-Retrieval Guardrail | If the database that stores our regulatory knowledge goes offline, the system currently breaks silently. This fix makes it detect the outage, warn the user, and still provide a safe response instead of a wrong one. | P1 | Guardrails / Reliability | If Neo4j is down, the exception handler fires before the zero-retrieval check. Guardrail won’t trigger; query passes through unmodified to LLM. | Add fallback behavior when Neo4j is unreachable: detect connection failure separately from zero-retrieval, show a specific “System Temporarily Unavailable” notice, log the Neo4j failure to audit DB, optionally fall back to KB-only retrieval with a degraded-mode notice. | adversarial_guardrails.md (line 124) | Small | Anmol | This is a continuity guardrail, prioritize this. | • PRIORITY: Separate connection failure from zero-retrieval • DONE: Neo4j health check + failover guardrail + user warning banner (v0.18.0, 14th Mar) | 7th March
7 | Confidence Score: Time-Decay Weighting | Older regulatory sections might be outdated or superseded. This feature would reduce the AI's confidence when it relies on older sources, encouraging it to flag answers that may need human verification. | Deferred | Confidence Scoring | All source sections weighted equally regardless of age or amendment date. | Penalize older sections slightly in confidence calculation. Requires amendment date metadata on Ch24Document nodes. | confidence_scoring.md (line 275) | Medium | — | To be rethinked | • DO NOT TOUCH — Too subjective. Soham: “Who plays God there?” Hardeep: “I wouldn’t touch it.” | Deferred indefinitely
8 | Confidence Score: Cross-Query Coherence | If the AI pulls up two regulatory sections that contradict each other, it should recognize the conflict and lower its confidence instead of confidently giving a potentially wrong answer. | P2 | Confidence Scoring | Each query scored independently. No cross-reference validation between retrieved sections. | Detect contradictions between retrieved sections and penalize confidence when sections conflict. Soham: “This is adversarial intelligence… a very important thing that should go into the confidence core.” | confidence_scoring.md (line 276) | Large | Anmol | Accepted | • Build contradiction detection between retrieved sections | TBD (P2)
9 | Confidence Score: User Feedback Loop | When users rate responses as helpful or unhelpful (thumbs up/down), those ratings feed back into the system to improve future answers — the AI learns what a good answer looks like over time. | P1 | Confidence Scoring | Weights are static (set once in v0.17.3). No mechanism for real-world calibration. | Allow user feedback (thumbs up/down) to fine-tune confidence weights over time. Store feedback in audit DB, run periodic weight optimization. Escalated P2→P1 because partially built and high-quality training signal. | confidence_scoring.md (lines 277-279) | Large | Anmol | Accepted, escalate to P1, prioritize, discuss with team and close the process no later than 5th March end of business. | • PRIORITY: Discuss with team, close by 5th March EOB | 5th March (decision) 12th March (implementation)
10 | Confidence Score: Explainability UI | Instead of just showing a confidence number, the system explains in plain English why it's confident or not — e.g., "High confidence: 4 regulatory sections agree on this limit." | P1 | Confidence Scoring / UX | Trace mode (show_trace=True) shows raw signal breakdown but it’s a developer-facing debug view, not user-friendly. | User-facing confidence explanation: natural language summary of which signals drove the score, displayed as a tooltip or expandable section. | confidence_scoring.md (line 278) | Small | Anmol | Accepted, this is great | • Design natural-language confidence explanation templates | 10th March
11 | Frontend Response Component | A polished chat interface that displays RegOS answers in a structured, professional format with color-coded compliance status, clickable source references, and clear section headers. | P2 | Frontend / UX | Enterprise formatting is pure markdown rendered by Open WebUI’s default message component. No custom UI. | Custom Svelte component that recognizes RegOS response format and renders: colored confidence badge, collapsible citation blocks, confidence gauge visualization, escalation banner with action buttons, structured refusal card. | P0_Feature_Analysis.md (lines 73-78) | Large | Shreya / Simi / Amritpal | See point 1, deffered for later | • Deferred — falls under Shreya’s UI turnaround (see item 1) | Follows item 1
12 | Multi-Facility Context Disambiguation | When an organization manages multiple facilities, the system tracks which facility you're asking about and asks for clarification if your question could apply to more than one. | P2 | Core Pipeline | Basic conversation-aware context exists. Documented in functions_README but not fully operational for multi-facility scenarios. | Full support for organizations managing multiple facilities. System tracks which facility the user is discussing, asks for clarification when ambiguous, maintains per-facility regulatory context. | functions_README.md (lines 94-95) | Medium | Anmol | Accepted | • Build facility tracking in conversation context | 14th March
13 | Onboarding Engagement Disclaimer | A one-time welcome message shown to new users explaining that RegOS is an AI assistant, not a licensed professional — similar to a terms-of-service acknowledgment before first use. | P1 | Legal / Compliance | Per-response disclaimers are conditional (3-state). No one-time service agreement disclaimer exists in the product. | One-time engagement-level disclaimer shown during onboarding/first use. Use the custom bubble facility in Open WebUI. Framed as a service agreement rather than per-response warning. | disclaimer_research.md (line 143) | Small | Anmol | Do this using the custom bubble facility in openwebui, a quick close. | • Use Open WebUI custom bubble facility — quick close | 7th March
14 | SCADA → Dashboard Real-Time Feed | Live sensor data from treatment plants (water quality, flow rates, equipment status) shown on a real-time monitoring screen that updates automatically as new readings come in. | P1 | Integration / Visualization | SCADA Streaming API (WebSocket + SSE + REST) is operational. SSE clients can subscribe to real-time determinations. But no consumer UI exists. | Connect SSE stream to a monitoring UI (Grafana or custom dashboard). Real-time compliance status updates as sensor readings come in. Breach alerts with audio/visual notifications. Historical trend charts. | REGOS_CHANGELOG.md (lines 463-498) | Medium | Anmol | Accepted | • Choose consumer UI (Grafana vs custom dashboard vs deferred Svelte) | 17th March
15 | APAS Telemetry: Full Effluent Sensor Activation | Connecting all the water quality sensors (pH, dissolved oxygen, chlorine, etc.) to the compliance system so it can automatically check every reading against regulatory limits — not just temperature. | P1 | Integration / SCADA | 8 metric mappings configured (1 evaluable: temperature). 14 effluent sensor templates exist in apas_metric_mappings.json but are inactive (evaluate: false). | Activate all 14 effluent sensor mappings. Break all IO into qty + UOM columns. Add UOM_Conversion table entity with universal conversion rules — standard enterprise software pattern. | REGOS_CHANGELOG.md (lines 511-515) apas_metric_mappings.json | Small | Anmol | Enterprise software does it using a separate table entity called UOM (unit of measurement) please break all IO into a qty and uom column for ease of readability both for human context and AI. Additional table needs to be included called UOM_Conversion with the rules of converting it from one unit to another, this should be universal. | • Design UOM (Unit of Measurement) table entity | 12th March
16 | Adversarial Test Suite Automation | An automated test suite that runs 28 tricky questions designed to try to break the AI's safety guardrails. Instead of testing manually one by one, this runs them all automatically and reports the results. | P1 | Testing / QA | 28 test queries documented in adversarial_guardrails.md. Manual execution — copy-paste each query and verify behavior. | Automated test runner. Chapter 24 is the perfect testing ground for adversarial technology. Execute all 28 queries via API, check against expected behavior, produce pass/fail report. | adversarial_guardrails.md (full document) | Medium | Anmol | Accepted | • Build automated test runner script | 14th March
17 | GIS Well Field Protection Zone Mapping | Given a street address, the system checks whether that location falls inside a protected wellfield zone using Miami-Dade's official boundary maps — important for determining which environmental rules apply. | P1 | Core Pipeline / GIS | No GIS capability exists. System cannot evaluate location-based regulatory requirements. | NOT using ArcGIS APIs. Cartesian coordinate geometry approach: store lat/long boundaries of wellfield protection zones from Miami-Dade Open Data Portal, geocode user address, do point-in-polygon with plain math. Define location hierarchies (state → county → district → city) where lower hierarchy coordinates must fall within higher hierarchy. Replicable globally. Estimated effort: half a day prompting + half a day testing. | Miami-Dade Open Data Portal — Wellfield Protection Zones | Medium | Anmol |  | • Extract wellfield boundary data from Miami-Dade Open Data Portal | 5th March
18 | RegOS API Exposure for External Platforms | Opening up RegOS as a service that other applications can call. Instead of only working through the chat interface, other platforms (like Shreya's NID system) can send questions and get compliance answers back. | P1 | Integration / API | RegOS is only accessible via Open WebUI chat interface. No external API for other applications to consume. | Expose betterhardeep.ai as an API service for Shreya’s NID platform and future integrations. Fire-and-forget pattern: ~3 sec becomes ~20 sec latency for backend sync. Free (self-hosted). Extend to any application via API keys. | Meeting transcript (Mar 2, 2026) — Soham | Small | Anmol |  | • Design API endpoint for RegOS query service | 10th March
19 | NotebookLM Benchmarking Exercise | A side-by-side comparison of RegOS against Google NotebookLM, ChatGPT, and Claude using the same regulatory questions — to demonstrate where RegOS provides more accurate, source-backed answers. | P1 | Testing / QA | No formal comparison exists between RegOS and alternative tools for the same regulatory content. | Benchmark RegOS responses against Google NotebookLM, GPT, and Claude using same Chapter 24 PDF and prompts. Apples-to-apples comparison. Soham: “That is a very good exercise and showing ourselves the mirror.” | Meeting transcript (Mar 2, 2026) — Soham/Hardeep | Small | Anmol / Hardeep |  | • Upload Chapter 24 PDF to Google NotebookLM | 7th March

## Summary (Priority + Date)
RegOS — P1 / P2 Backlog Summary (Anmol Pokhriyal)
Sorted by priority then deadline. Last updated: 03 Mar 2026
# | Feature | Description | Priority | Owner | Complexity | Key Tasks | Deadline
— P1 —
3 | Escalation Workflow (Manual Trigger + Resolution + Routing) | When the AI is unsure about an answer, a human expert can be notified via email to review it. This includes a button in chat to manually flag a response, plus a system to track and resolve flagged cases. | P1 | Soham | Medium | • Phase 1: Email escalation button | Phase 1: 7th March Phase 2: 14th March
5 | Advanced Prompt Injection Defense + Smarter Guardrail Keyword Matching | Protection against users trying to trick the AI into ignoring its rules or giving incorrect answers. Also makes the system smarter about recognizing which questions are actually about regulations vs. off-topic. | P1 | Anmol | Medium | • Debate ease of deployment — implement by EOB 10th March or defer P2 | 10th March EOB (or defer to P2)
6 | Neo4j Failover for Zero-Retrieval Guardrail | If the database that stores our regulatory knowledge goes offline, the system currently breaks silently. This fix makes it detect the outage, warn the user, and still provide a safe response instead of a wrong one. | P1 | Anmol | Small | • PRIORITY: Separate connection failure from zero-retrieval | 7th March | DONE — 14th Mar
9 | Confidence Score: User Feedback Loop | When users rate responses as helpful or unhelpful (thumbs up/down), those ratings feed back into the system to improve future answers — the AI learns what a good answer looks like over time. | P1 | Soham | Large | • PRIORITY: Discuss with team, close by 5th March EOB | 5th March (decision) 12th March (implementation)
10 | Confidence Score: Explainability UI | Instead of just showing a confidence number, the system explains in plain English why it's confident or not — e.g., "High confidence: 4 regulatory sections agree on this limit." | P1 | Anmol | Small | • Design natural-language confidence explanation templates | 10th March
13 | Onboarding Engagement Disclaimer | A one-time welcome message shown to new users explaining that RegOS is an AI assistant, not a licensed professional — similar to a terms-of-service acknowledgment before first use. | P1 | Anmol | Small | • Use Open WebUI custom bubble facility — quick close | 7th March
14 | SCADA → Dashboard Real-Time Feed | Live sensor data from treatment plants (water quality, flow rates, equipment status) shown on a real-time monitoring screen that updates automatically as new readings come in. | P1 | Anmol | Medium | • Choose consumer UI (Grafana vs custom dashboard vs deferred Svelte) | 17th March
15 | APAS Telemetry: Full Effluent Sensor Activation | Connecting all the water quality sensors (pH, dissolved oxygen, chlorine, etc.) to the compliance system so it can automatically check every reading against regulatory limits — not just temperature. | P1 | Anmol | Small | • Design UOM (Unit of Measurement) table entity | 12th March
16 | Adversarial Test Suite Automation | An automated test suite that runs 28 tricky questions designed to try to break the AI's safety guardrails. Instead of testing manually one by one, this runs them all automatically and reports the results. | P1 | Anmol | Medium | • Build automated test runner script | 14th March
17 | GIS Well Field Protection Zone Mapping | Given a street address, the system checks whether that location falls inside a protected wellfield zone using Miami-Dade's official boundary maps — important for determining which environmental rules apply. | P1 | Shreya | Medium | • Extract wellfield boundary data from Miami-Dade Open Data Portal | 5th March
18 | RegOS API Exposure for External Platforms | Opening up RegOS as a service that other applications can call. Instead of only working through the chat interface, other platforms (like Shreya's NID system) can send questions and get compliance answers back. | P1 | Anmol | Small | • Design API endpoint for RegOS query service | 10th March
19 | NotebookLM Benchmarking Exercise | A side-by-side comparison of RegOS against Google NotebookLM, ChatGPT, and Claude using the same regulatory questions — to demonstrate where RegOS provides more accurate, source-backed answers. | P1 | Soham | Small | • Upload Chapter 24 PDF to Google NotebookLM | 7th March
— P2 —
1 | Compliance Dashboard UI | A visual dashboard that shows at a glance whether the facility is meeting all regulatory requirements — green for compliant, amber for borderline, red for violations. | P2 | Shreya | Large | • DO NOT TOUCH — Shreya leads UI/UX direction | 5th March (direction from team)
11 | Frontend Response Component | A polished chat interface that displays RegOS answers in a structured, professional format with color-coded compliance status, clickable source references, and clear section headers. | P2 | Shreya / Simi / Amritpal | Large | • Deferred — falls under Shreya’s UI turnaround (see item 1) | Follows item 1
2 | Chat-Based Audit Query Interface | Instead of running database queries, users can simply ask questions in plain English like "Show me all queries from last week" and get audit results back in a chat conversation. | P2 | Anmol | Medium | • Create Open WebUI Tool/Pipe for audit DB queries | TBD (P2)
4 | Multi-Jurisdiction Support | Right now the system only knows Miami-Dade County rules. This feature would let it understand regulations from other counties, states, or jurisdictions so it can serve a wider customer base. | P2 | TBD | Very Large | • Stakeholder engagement to define future scope | TBD (P2)
12 | Multi-Facility Context Disambiguation | When an organization manages multiple facilities, the system tracks which facility you're asking about and asks for clarification if your question could apply to more than one. | P2 | Anmol | Medium | • Build facility tracking in conversation context | 14th March
8 | Confidence Score: Cross-Query Coherence | If the AI pulls up two regulatory sections that contradict each other, it should recognize the conflict and lower its confidence instead of confidently giving a potentially wrong answer. | P2 | Anmol | Large | • Build contradiction detection between retrieved sections | TBD (P2)
— Deferred —
7 | Confidence Score: Time-Decay Weighting | Older regulatory sections might be outdated or superseded. This feature would reduce the AI's confidence when it relies on older sources, encouraging it to flag answers that may need human verification. | Deferred | — | Medium | • DO NOT TOUCH — Too subjective. Soham: “Who plays God there?” Hardeep: “I wouldn’t touch it.” | Deferred indefinitely
RegOS — APAS Group — Confidential
Total: 19 features ¦ P1: 12 ¦ P2: 6 ¦ Deferred: 1

## P0 Completed (Reference)
P0 Features — Completed and Deployed
# | Feature | Version | Implementation | Key Capability | Status
1 | Audit Logging | v0.4.0 | audit_logger.py (Filter) | SQLite DB, tamper-evident SHA-256 hashing, confidence/escalation/guardrail metadata capture | Done
2 | GraphRAG Pipeline | v0.17.3 | graphrag_filter.py (Filter) | 4-step retrieval: document fulltext → entity traversal → concept expansion → direct search. FEA v2 graph (693 nodes, 2,351 rels) | Done
3 | Confidence Scoring | v0.17.3 | graphrag_filter.py (Filter) | 6-signal weighted composite (avg_doc 0.30, doc_count 0.15, concept 0.25, sections 0.12, graph_exclusive 0.10, direct 0.08) | Done
4 | Enterprise Output Formatting | v0.7.0+ | system_prompt.md + Filter | 3 personas (Citizen, Consultant, Regulator), structured template, expert-informed design | Done
5 | Sources Panel Integration | v0.8.0 | graphrag_filter.py (Outlet) | [G1]-[G5] citations in Sources button alongside KB sources. Direct outlet mutation pattern. | Done
6 | Conditional Disclaimers | v0.8.1 | graphrag_filter.py (Outlet) | 3-state confidence-adaptive: HIGH (minimal), MEDIUM (acknowledges gaps), LOW (honest about limits). No "consult professionals" | Done
7 | Escalation Workflow | v0.10.0 | graphrag_filter.py + n8n | Auto-flag on low confidence, n8n webhook with full case packet, AI case brief generation, structured user notice | Done
8 | Threshold Evaluation | v0.14.0 | graphrag_filter.py (Inlet) | Regex detection for 35+ parameters, 96 Ch.24 thresholds, SHA-256 evidence hashing, compliance badge, breach DB | Done
9 | Guardrails & Refusal | v0.12.0 | graphrag_filter.py (Inlet/Outlet) | Out-of-scope keywords, jurisdiction mismatch (countries + US states), zero-retrieval detection, professional notices with ref IDs | Done
10 | SCADA Streaming API | v0.1.0 | api/scada_stream.py | WebSocket + SSE + REST batch ingestion, token-bucket rate limiting, real-time threshold evaluation, 15 tests passing | Done
11 | APAS Telemetry Bridge | v0.1.0 | api/apas_bridge.py | Polling bridge with JWT auth, metric mapping registry, unit conversion, exponential backoff, 12 tests passing | Done