## P1-P2 Feature Backlog
RegOS — Deferred Features (P1 / P2 / Future)
Post-meeting update (Mar 2, 2026). Items 4+5 merged into 3. GIS scope rewritten. Time-Decay deferred. API Exposure + NotebookLM Benchmark added.
# | Feature | Phase | Category | Current State in P0 | What Was Planned | Source Document | Complexity | Owner | Task / Subtask | Deadline
1 | Compliance Dashboard UI | P2 | Frontend / Visualization | Deprioritized. Replaced by SCADA Streaming API (v0.1.0) as primary integration point. No UI exists. | Single-page dashboard showing: compliance status (green/amber/red), active breach alerts list, embedded RegOS chat interface, aggregated trend charts. Would consume data from threshold evaluation API, breach DB, and audit records. | P0_Feature_Analysis.md (lines 163-186) REGOS_CHANGELOG.md (line 297) | Large | Shreya | • DO NOT TOUCH — Shreya leads UI/UX direction | 5th March (direction from team)
◦ Team to present UI direction by 5th March
◦ Component library and button behaviors defined first
◦ Simi + Amritpal assist with layout/mockups
• After Shreya’s framework is ready:
◦ Define data sources (breach DB, audit API, threshold API)
◦ Build compliance status page
◦ Connect to SCADA SSE stream for real-time updates
2 | Chat-Based Audit Query Interface | P2 | Audit / UX | Basic REST API exists (GET /api/audit/records with query_id, user_id, date_range filters). Terminal/API-only access. | Full conversational interface for querying audit logs. Users would ask natural-language questions like “Show me all escalated queries from last week” and get structured results in the chat. Would require a dedicated Open WebUI Tool or Pipe that queries the audit SQLite DB. | P0_Feature_Analysis.md (line 154) | Medium | Anmol | • Create Open WebUI Tool/Pipe for audit DB queries | TBD (P2)
◦ Define supported query types (by date, user, escalation status)
◦ Build SQLite query builder from natural language
◦ Format results as structured chat response
• Add date range, user, and query_id filters
• Test with sample queries (“show escalated queries last week”)
• Register as a Tool in Open WebUI admin
3 | Escalation Workflow (Manual Trigger + Resolution + Routing) | P1 | Escalation Workflow | Only automatic escalation exists (confidence < 0.65). Cases go to n8n webhook but never come back as resolved. n8n Branch 1 ends with No-Op placeholder. Response captured but not displayed to users. | Two-phase approach. Phase 1: simple email escalation button (font-awesome icon next to thumbs up/TTS in response subtext panel) that emails sysadmin1@regos.ai with chat context. Uses chat_ID for traceability. Phase 2: full Jira integration (3 free seats, lifetime) — push entire chat context + form + relevant docs into Jira helpdesk. Case lifecycle: Open → In Review → Resolved → Closed. Display resolution status back to user via status API. | REGOS_CHANGELOG.md (lines 257, 259) N8N_ESCALATION_SETUP.md (lines 205, 207-216) | Medium | Anmol | • Phase 1: Email escalation button | Phase 1: 7th March Phase 2: 14th March
◦ Add font-awesome flag icon to response subtext panel (next to thumbs up, TTS)
◦ Wire click to send email to sysadmin1@regos.ai
◦ Include full chat context + chat_ID in email body
◦ Log manual escalation event to audit DB
• Phase 2: Jira integration
◦ Set up Jira project (3 free seats, full features)
◦ Build OpenWebUI API → Jira ticket creation (fire-and-forget)
◦ Push chat context + form + documents into Jira
◦ Implement case lifecycle (Open → In Review → Resolved → Closed)
• Status API integration
◦ Endpoint to fetch case status by chat_ID
◦ Display resolution status in chat interface
• Notify original user when case is resolved
4 | Multi-Jurisdiction Support | P2 | Knowledge Graph / Core | System is scoped exclusively to Miami-Dade County Chapter 24. Jurisdiction guardrail blocks non-Miami-Dade queries. | Support multiple regulatory jurisdictions (other Florida counties, other states, federal EPA). Would require: separate knowledge graphs per jurisdiction, jurisdiction detection and routing in inlet, cross-jurisdiction comparison queries, per-jurisdiction confidence thresholds, jurisdiction-specific threshold tables. | REGOS_CHANGELOG.md (line 318) adversarial_guardrails.md (line 120) | Very Large | TBD | • Stakeholder engagement to define future scope | TBD (P2)
◦ Identify target jurisdictions (FL counties, other states, federal)
◦ Assess regulatory data availability per jurisdiction
• Design multi-graph architecture
◦ Separate Neo4j DB or namespaced graph per jurisdiction
◦ Jurisdiction detection + routing in inlet
• Build per-jurisdiction threshold tables
• Cross-jurisdiction comparison query support
• Update guardrail to allow supported jurisdictions
5 | Advanced Prompt Injection Defense + Smarter Guardrail Keyword Matching | P1 | Guardrails / Security | Prompt injection defense relies entirely on system prompt instructions. No hard programmatic defenses. Keyword matching is blunt — “building code” triggers even if user asks about Chapter 24 facilities near buildings. | Add programmatic injection detection: pattern matching for common injection techniques, input sanitization layer before graph search, canary token detection, output validation. Replace simple substring matching with context-aware detection: NLP-based intent classification, phrase boundary awareness, configurable false-positive tolerance. | adversarial_guardrails.md (lines 118, 122-123) | Medium | Anmol | • Debate ease of deployment — implement by EOB 10th March or defer P2 | 10th March EOB (or defer to P2)
• Build pattern-matching injection detector
◦ Regex for “ignore previous instructions”, “you are now”, etc.
◦ Role-play attack detection
• Input sanitization layer (pre-graph-search)
• Replace blunt keyword matching with context-aware detection
◦ NLP intent classification
◦ Phrase boundary awareness
◦ Configurable false-positive tolerance
• Output validation for information leakage
• Run against existing 4 adversarial injection test cases
6 | Neo4j Failover for Zero-Retrieval Guardrail | P1 | Guardrails / Reliability | If Neo4j is down, the exception handler fires before the zero-retrieval check. Guardrail won’t trigger; query passes through unmodified to LLM. | Add fallback behavior when Neo4j is unreachable: detect connection failure separately from zero-retrieval, show a specific “System Temporarily Unavailable” notice, log the Neo4j failure to audit DB, optionally fall back to KB-only retrieval with a degraded-mode notice. | adversarial_guardrails.md (line 124) | Small | Anmol | • PRIORITY: Separate connection failure from zero-retrieval | 7th March
◦ Catch Neo4j ConnectionError distinctly
◦ Don’t let it fall through to zero-retrieval guardrail
• Show “System Temporarily Unavailable” notice on Neo4j failure
• Log Neo4j failure event to audit DB
• Optional: fall back to KB-only retrieval with degraded-mode notice
• Add health-check endpoint for Neo4j connection status
7 | Confidence Score: Time-Decay Weighting | Deferred | Confidence Scoring | All source sections weighted equally regardless of age or amendment date. | Penalize older sections slightly in confidence calculation. Requires amendment date metadata on Ch24Document nodes. | confidence_scoring.md (line 275) | Medium | — | • DO NOT TOUCH — Too subjective. Soham: “Who plays God there?” Hardeep: “I wouldn’t touch it.” | Deferred indefinitely
• If revisited in the future:
◦ Evaluate whether amendment dates are obtainable
◦ Assess impact on scoring accuracy vs complexity
◦ Calibrate decay rate against known regulatory updates
8 | Confidence Score: Cross-Query Coherence | P2 | Confidence Scoring | Each query scored independently. No cross-reference validation between retrieved sections. | Detect contradictions between retrieved sections and penalize confidence when sections conflict. Soham: “This is adversarial intelligence… a very important thing that should go into the confidence core.” | confidence_scoring.md (line 276) | Large | Anmol | • Build contradiction detection between retrieved sections | TBD (P2)
◦ Identify overlapping parameter references across sections
◦ Flag conflicting values (e.g. 30 mg/L vs 15 mg/L)
• Penalize confidence when sections conflict
• Generate user-facing note explaining the distinction
• Test with known Chapter 24 section overlaps (24-42 vs 24-42.1)
9 | Confidence Score: User Feedback Loop | P1 | Confidence Scoring | Weights are static (set once in v0.17.3). No mechanism for real-world calibration. | Allow user feedback (thumbs up/down) to fine-tune confidence weights over time. Store feedback in audit DB, run periodic weight optimization. Escalated P2→P1 because partially built and high-quality training signal. | confidence_scoring.md (lines 277-279) | Large | Anmol | • PRIORITY: Discuss with team, close by 5th March EOB | 5th March (decision) 12th March (implementation)
• Add thumbs up/down feedback capture in outlet
◦ Hook into Open WebUI’s existing rating mechanism
◦ Store feedback in audit DB (query_id, rating, timestamp)
• Build periodic weight optimization script
◦ Pull feedback data from audit DB
◦ Correlate ratings with confidence signals
◦ Output updated signal weights
• Per-domain threshold tuning for different query types
10 | Confidence Score: Explainability UI | P1 | Confidence Scoring / UX | Trace mode (show_trace=True) shows raw signal breakdown but it’s a developer-facing debug view, not user-friendly. | User-facing confidence explanation: natural language summary of which signals drove the score, displayed as a tooltip or expandable section. | confidence_scoring.md (line 278) | Small | Anmol | • Design natural-language confidence explanation templates | 10th March
◦ HIGH: “High confidence — X sections directly address your question”
◦ MEDIUM: “Medium confidence — limited sections found”
◦ LOW: “Low confidence — may not cover all aspects”
• Map each scoring signal to a plain-English phrase
• Inject explanation as tooltip or expandable section in outlet
• Test across HIGH/MEDIUM/LOW band queries
11 | Frontend Response Component | P2 | Frontend / UX | Enterprise formatting is pure markdown rendered by Open WebUI’s default message component. No custom UI. | Custom Svelte component that recognizes RegOS response format and renders: colored confidence badge, collapsible citation blocks, confidence gauge visualization, escalation banner with action buttons, structured refusal card. | P0_Feature_Analysis.md (lines 73-78) | Large | Shreya / Simi / Amritpal | • Deferred — falls under Shreya’s UI turnaround (see item 1) | Follows item 1
• When ready:
◦ Build custom Svelte message component
◦ Colored confidence badge (green/amber/red)
◦ Collapsible citation blocks
◦ Escalation banner with action buttons
◦ Structured refusal card
12 | Multi-Facility Context Disambiguation | P1 | Core Pipeline | Basic conversation-aware context exists. Documented in functions_README but not fully operational for multi-facility scenarios. | Full support for organizations managing multiple facilities. System tracks which facility the user is discussing, asks for clarification when ambiguous, maintains per-facility regulatory context. | functions_README.md (lines 94-95) | Medium | Anmol | • Build facility tracking in conversation context | 14th March
◦ Extract facility name/location from user messages
◦ Store active facility in session state
• Disambiguation prompt when facility is ambiguous
• Per-facility regulatory context lookup
• Test with multi-facility scenario (“Miami Beach plant BOD 45 — what about Homestead?”)
13 | Onboarding Engagement Disclaimer | P1 | Legal / Compliance | Per-response disclaimers are conditional (3-state). No one-time service agreement disclaimer exists in the product. | One-time engagement-level disclaimer shown during onboarding/first use. Use the custom bubble facility in Open WebUI. Framed as a service agreement rather than per-response warning. | disclaimer_research.md (line 143) | Small | Anmol | • Use Open WebUI custom bubble facility — quick close | 7th March
◦ Identify custom bubble config in Open WebUI settings
◦ Add one-time engagement disclaimer on first chat
• Draft disclaimer text (Option D from disclaimer_research.md)
• Frame as service agreement, not per-response warning
• Test: new user sees disclaimer once, returning user does not
14 | SCADA → Dashboard Real-Time Feed | P1 | Integration / Visualization | SCADA Streaming API (WebSocket + SSE + REST) is operational. SSE clients can subscribe to real-time determinations. But no consumer UI exists. | Connect SSE stream to a monitoring UI (Grafana or custom dashboard). Real-time compliance status updates as sensor readings come in. Breach alerts with audio/visual notifications. Historical trend charts. | REGOS_CHANGELOG.md (lines 463-498) | Medium | Anmol | • Choose consumer UI (Grafana vs custom dashboard vs deferred Svelte) | 17th March
• Connect SSE stream to chosen UI
◦ Subscribe to real-time compliance determinations
◦ Render breach alerts with audio/visual notifications
• Build historical trend charts from breach DB
• Test end-to-end: SCADA reading → threshold eval → dashboard alert
15 | APAS Telemetry: Full Effluent Sensor Activation | P1 | Integration / SCADA | 8 metric mappings configured (1 evaluable: temperature). 14 effluent sensor templates exist in apas_metric_mappings.json but are inactive (evaluate: false). | Activate all 14 effluent sensor mappings. Break all IO into qty + UOM columns. Add UOM_Conversion table entity with universal conversion rules — standard enterprise software pattern. | REGOS_CHANGELOG.md (lines 511-515) apas_metric_mappings.json | Small | Anmol | • Design UOM (Unit of Measurement) table entity | 12th March
◦ Break all IO into qty + uom columns
◦ Define UOM codes (mg/L, °C, NTU, CFU/100mL, etc.)
• Build UOM_Conversion table (universal)
◦ Define conversion rules between units
◦ Ensure bidirectional conversion support
• Activate 14 effluent sensor mappings
◦ Verify unit conversion for each metric
◦ Cross-reference against threshold table entries
◦ Set evaluate: true in apas_metric_mappings.json
• Test each sensor with sample APAS telemetry data
16 | Adversarial Test Suite Automation | P1 | Testing / QA | 28 test queries documented in adversarial_guardrails.md. Manual execution — copy-paste each query and verify behavior. | Automated test runner. Chapter 24 is the perfect testing ground for adversarial technology. Execute all 28 queries via API, check against expected behavior, produce pass/fail report. | adversarial_guardrails.md (full document) | Medium | Anmol | • Build automated test runner script | 14th March
◦ Read all 28 queries from adversarial_guardrails.md
◦ Execute each via Open WebUI API
• Define expected behavior per query
◦ Expected guardrail type (scope/jurisdiction/zero-retrieval)
◦ Expected confidence band
◦ Expected escalation status
• Query audit DB to verify each result
• Generate pass/fail report
• Integrate into deployment pipeline for regression testing
17 | GIS Well Field Protection Zone Mapping | P1 | Core Pipeline / GIS | No GIS capability exists. System cannot evaluate location-based regulatory requirements. | NOT using ArcGIS APIs. Cartesian coordinate geometry approach: store lat/long boundaries of wellfield protection zones from Miami-Dade Open Data Portal, geocode user address, do point-in-polygon with plain math. Define location hierarchies (state → county → district → city) where lower hierarchy coordinates must fall within higher hierarchy. Replicable globally. Estimated effort: half a day prompting + half a day testing. | Miami-Dade Open Data Portal — Wellfield Protection Zones | Medium | Anmol | • Extract wellfield boundary data from Miami-Dade Open Data Portal | 5th March
◦ Download wellfield maps, boundaries, zip codes, contour lines
◦ Extract Cartesian coordinates for each zone polygon
◦ Understand wellfield travel time contour data
• Build location hierarchy model
◦ Define hierarchy: State → County → District → City
◦ Store coordinates at each level
◦ Validate lower coords fall within higher coords
• Implement point-in-polygon checker (Cartesian math, no GIS API)
◦ Geocode user-provided address to lat/long
◦ Check if point falls within wellfield zone boundaries
◦ Return zone name + applicable Chapter 24 restrictions
• Integrate into RegOS chat flow
◦ Detect address-based queries in inlet
◦ Run coordinate check and inject result into LLM context
◦ Format response with zone determination + regulatory implications
• Add wellfield data to knowledge graph (separate from main RAG)
18 | RegOS API Exposure for External Platforms | P1 | Integration / API | RegOS is only accessible via Open WebUI chat interface. No external API for other applications to consume. | Expose betterhardeep.ai as an API service for Shreya’s NID platform and future integrations. Fire-and-forget pattern: ~3 sec becomes ~20 sec latency for backend sync. Free (self-hosted). Extend to any application via API keys. | Meeting transcript (Mar 2, 2026) — Soham | Small | Anmol | • Design API endpoint for RegOS query service | 10th March
◦ Define request/response schema (query, context, auth)
◦ Implement API key authentication
◦ Fire-and-forget pattern for backend sync
• Expose via betterhardeep.ai domain
• Test with Shreya’s NID platform as first consumer
• Document API for future integrations
19 | NotebookLM Benchmarking Exercise | P1 | Testing / QA | No formal comparison exists between RegOS and alternative tools for the same regulatory content. | Benchmark RegOS responses against Google NotebookLM, GPT, and Claude using same Chapter 24 PDF and prompts. Apples-to-apples comparison. Soham: “That is a very good exercise and showing ourselves the mirror.” | Meeting transcript (Mar 2, 2026) — Soham/Hardeep | Small | Anmol / Hardeep | • Upload Chapter 24 PDF to Google NotebookLM | 7th March
• Run identical prompts through:
◦ RegOS (betterhardeep.ai)
◦ Google NotebookLM
◦ ChatGPT (raw, no RAG)
◦ Claude (raw, no RAG)
• Compare outputs: accuracy, citations, structure, depth
• Document strengths/weaknesses of each
• Use findings to improve RegOS system prompt and retrieval

## Summary by Phase
Feature Count by Phase and Category
Phase | Count | Categories | Complexity Breakdown | Key Dependencies
P1 | 13 | Confidence Scoring (1), Confidence Scoring / UX (1), Core Pipeline (1), Core Pipeline / GIS (1), Escalation Workflow (1), Guardrails / Reliability (1), Guardrails / Security (1), Integration / API (1), Integration / SCADA (1), Integration / Visualization (1), Legal / Compliance (1), Testing / QA (2) | Large: 1, Medium: 6, Small: 6 | Jira (3 free seats), n8n webhooks, APAS Telemetry API, Open WebUI API, Miami-Dade Open Data Portal
P2 | 5 | Audit / UX (1), Confidence Scoring (1), Frontend / UX (1), Frontend / Visualization (1), Knowledge Graph / Core (1) | Large: 3, Medium: 1, Very Large: 1 | Svelte frontend build pipeline, multi-jurisdiction knowledge graphs, Shreya’s UI framework
Deferred | 1 | Confidence Scoring (1) | Medium: 1 | Explicitly shelved by leadership
Total | 19

## P0 Completed (Reference)
P0 Features — Completed and Deployed
# | Feature | Version | Implementation | Key Capability | Status
1 | Audit Logging | v0.4.0 | audit_logger.py (Filter) | SQLite DB, tamper-evident SHA-256 hashing, confidence/escalation/guardrail metadata capture | Done
2 | GraphRAG Pipeline | v0.17.3 | graphrag_filter.py (Filter) | 4-step retrieval: document fulltext → entity traversal → concept expansion → direct search. FEA v2 graph (693 nodes, 2,351 rels) | Done
3 | Confidence Scoring | v0.17.3 | graphrag_filter.py (Filter) | 6-signal weighted composite (avg_doc 0.30, doc_count 0.15, concept 0.25, sections 0.12, graph_exclusive 0.10, direct 0.08) | Done
4 | Enterprise Output Formatting | v0.7.0+ | system_prompt.md + Filter | 3 personas (Citizen, Consultant, Regulator), structured template, expert-informed design | Done
5 | Sources Panel Integration | v0.8.0 | graphrag_filter.py (Outlet) | [G1]-[G5] citations in Sources button alongside KB sources. Direct outlet mutation pattern. | Done
6 | Conditional Disclaimers | v0.8.1 | graphrag_filter.py (Outlet) | 3-state confidence-adaptive: HIGH (minimal), MEDIUM (acknowledges gaps), LOW (honest about limits). No "consult professionals" | Done
7 | Escalation Workflow | v0.10.0 | graphrag_filter.py + n8n | Auto-flag on low confidence, n8n webhook with full case packet, AI case brief generation, structured user notice | Done
8 | Threshold Evaluation | v0.14.0 | graphrag_filter.py (Inlet) | Regex detection for 35+ parameters, 96 Ch.24 thresholds, SHA-256 evidence hashing, compliance badge, breach DB | Done
9 | Guardrails & Refusal | v0.12.0 | graphrag_filter.py (Inlet/Outlet) | Out-of-scope keywords, jurisdiction mismatch (countries + US states), zero-retrieval detection, professional notices with ref IDs | Done
10 | SCADA Streaming API | v0.1.0 | api/scada_stream.py | WebSocket + SSE + REST batch ingestion, token-bucket rate limiting, real-time threshold evaluation, 15 tests passing | Done
11 | APAS Telemetry Bridge | v0.1.0 | api/apas_bridge.py | Polling bridge with JWT auth, metric mapping registry, unit conversion, exponential backoff, 12 tests passing | Done